## Risk
1. Write the index number and the name of each team member below
(First name Last Name, index no.)
Maria Musiał 156062
Wiktoria Szarzyńska 156058
Lidia Wiśniewska 156063
Joanna Szczublińska 156070
2. Then focus on identifying risk factors and writing them down in the table below (don't assess them just write them down!)
3. Assess the likelihood and impact of the risk (default 3-point scale is used)
4. Next evaluate the importance of the risks (based on probability and impact - sort the risks beginning from the most important)
5. Starting with the most important risks, describe how you intend to respond to a given risk
Risk | Probability | Impact | Importance | Response
No programming skills in Java. | Medium | High | High | Reduce: youtube tutorials, reading books, asking for help.
No knowledge about frameworks and tools required for the project. | High | High | High | Reduce: youtube tutorials, reading books, asking for help, listening more carefully on laboratories and lectures.
Loss of internet. | Medium | Medium | High | Reduce: use laboratory devices, work in person.
Misunderstanding the project. | Low | High | Medium | Reduce: asking for help, attending on office hours.
Poor time management. | Low | Medium | Medium | Accept: accept the probability of lower grade or three all nighters in a row.
Hardware issues. | Low | Medium | Medium | Reduce: use laboratory devices.
Lack of soft skills, communication problems. | Low | Medium | Medium | Avoid: avoid conflicts, try to focus on your part.
Losing team member. | Low | Medium | Medium | Fallback: divide the work assesed to others.
Unexpected illness (Maria in hospital). | Medium | Low | Low | Fallback: other means of communication.
Unexpected accident. | Low | Low | Low | Accept: delay completion time.
Tests on the other university. | High | Low | Low | Fallback: divide the work assesed to others.

## Scale
High
Medium
Low